## Slide 1: Program Review Workshop April 7, 2025
An overview of the process and the timeline

## Slide 2: Scope of the Self-Study
All Programs
All Levels
All Modalities
All Locations
All Students

## Slide 3: Timeline: Prior Year (i.e. now)
Spring – Form your working group, outline a plan and identify initial data needs – connect with Pam if you have questions
Spring – Connect with Cate if you plan to use the P&SS platform
Spring – IRP creates a Blackboard shell and loads resources and data
  Note that IRP will update the trend data in the fall

## Slide 4: Deadlines: Self-Study Year
September 30 – Preferred deadline for additional data requests
January 15 – Draft of self-study due to the Dean(s)
February 1 – External evaluator names (3) due to the Dean
February 1 – Dean(s) meet with Chairs to discuss revisions/clarifications
March 1 – Final self-study report due to the Provost, Dean(s) and Director of Assessment.

## Slide 5: Timeline: Following Year
September – Meet with Provost, Dean(s) and Director of Assessment to review evaluator’s report
December - Meet with Provost, Dean(s) and Director of Assessment to review Final Action Plan
Run any curricular changes through governance

## Slide 6: External Evaluator Timeline
February 1 –Chair forwards the name, address and CV of potential external evaluators (3) to the Dean
February – Dean and Director of Assessment review evaluators
March – IRP completes the contract process and forwards the completed self-study report to the external evaluator
April – The external evaluator completes an on-site visit
  Before setting the site visit – make sure all parties are available!
May – The external evaluator submits a report to IRP. IRP will forward to Provost, Dean(s), and Chair and release payment to evaluator.

## Slide 7: Dean’s Timeline
January - Review self-study draft utilizing the rubric
February – Meet with the Chair
February - Select the external evaluator in consultation with the Director of Assessment
April - Meet with the external evaluator during on-site visit
September - Meet with Provost, Chair and Director of Assessment to review the external evaluator’s report
December - Meet with Provost, Chair and Director of Assessment to review the Final Action Plan

## Slide 8: Resources
AUC 176 - Program Review Guidelines
Pilot Template #1
Director of Assessment
Dean(s)
AVP IRP – Data Needs
Blackboard
Planning & Self Study/Program Review Video and Support Documentation

## Slide 9: Program Review Guidelines: AUC 176
1. Self-Study Overview
2. Self-Study Outline and Guidance
3. External Evaluator Selection and Guidelines
4. Final Action Plan

## Slide 10: Components of the Self-Study Report
Executive Summary
Overview and Vision
Assessment
Analysis and Action Plan for the Future
Appendices (if not incorporated into body of document)
  Student Data
  Faculty Data
  Resources

## Slide 11: Overview and Vision
Programs Vision, Mission, and objectives
Overview of Program (degree requirements, breadth and depth of Program)
Internal demand of program
Recommendations and actions from previous review
Initiatives and changes in Last five Years

## Slide 12: Assessment
Program inputs
  Program Reputation
  Students
  Faculty, Staff, Resources
Program processes
  Curriculum
  Students, Faculty, Quality Improvement Initiatives
Program Outcomes
  Program
  Student

## Slide 13: Assessment Tips
Request data early
If you plan on doing your own data collection; do this early
After reflecting on data, develop a process by which you can close the loop (What changes would you make as a result of this data?)
Reflect on how your data collection points towards possible new avenues for data collection? (Indirect Assessment, Direct Assessment)
Develop a basis for what direction an Assessment Plan would take. (Do you need to revise your learning outcome statements, for example).

## Slide 14: Analysis and Preliminary Action Plan for the Future (Self Identified)
Comparative strengths and distinctiveness and areas of improvement across all program levels
Opportunities to extend strengths and resources
Weaknesses and the opportunities to address them
Positioning of program
creation of draft Action Plan for next 5 years

## Slide 15: Final Action Plan
Informed by external evaluators report and self-study
Use Table Format described in AUC176 to include the following:
  Specific area where improvement is needed
  Evidence supporting recommended changes
  The proposed timeline for implementing the change(s)
  The people who will implement the change(s)
  The resources needed to successfully implement the change(s)
  A plan to assess the change after implementation.

## Slide 16: Additional Thoughts
  AUC 176 serves to provide guidelines for program review
  Every item may not apply to your program and additional items may do a better job of telling your story
  Use a template/outline that best suits your needs
  The ultimate goal is to have a meaningful self-study

## Slide 17: Planning & Self Study for Program Review
Watermark Support Pages: Program Review as a Contributor
https://support.watermarkinsights.com/hc/en-us/articles/4706611548443-Program-Review-as-a-Contributor
Introductory Instructional Video for Program Review
https://fitchburgstate.screencasthost.com/watch/cTerlOniFWj

## Slide 18: Discussion and Questions